## Reports
Week | What did you do this week? | What will you do next week? | Anything blocking your progress? | Would you like to schedule a discussion? | Preferred meeting time
4 | Product backlog for program and technologies - languages section | Start coding | AI Practical 1 was but not anymore | No | 11:00
4 | *Super group meeting about authentication *analysis of front end tools | Start programing | deadline - on Friday | Yes | 10:00
4 | Write report for deliverable 1. | Deciding implementation techniques and allocation of tasks with team mates. Start to write initial unit tests for everybody to describe aspects of our backlog. | I might have to focus on my two practicals due week 5, but I will try do get my tasks done. | No | 11:00
4 | - Scrum Meeting - Write Scrum section of the report for Deliverable 1 | - Start working on the database design - Add schema for database design | No | Yes | 11:00
4 | Filled in core requirements, additional requirements, setup the gitlab. Doing overview of semester 1 plan after scrum meeting, problems we may have with development | Will be discussed in scrum meeting | Deadlines? | Yes | 11:00
5 | Server-side input validation for register, minor fixes, customErrors.js and validate.js | register users server side + post input validation | no | Yes | 10:00
5 | - Database design for users and posts - Testing of the database - Set up database on MariaDB | - Create database getter and setter functions - Debugging and testing | No | Yes | 11:00
5 | Completed Register fully and begun looking at the front end | overhaul the filespace and code for frontend | no | Yes | 10:00
5 | Database design; Agent/Proxy Design mode | Database and server connection. | N/A | No | 1:01
6 | Worked on front-end to create basic user interface and establish communication between client and server to enable users to be registered | Work on front-end to enable user to submit code | Nothing massive | No | 11:00
6 | - Researched the generation of unique user IDs | - Backend of the login form for the user | No | Yes | 11:00
6 | Database setup; Users table setup and basic users operation. | Provide more functionalities of database; interacting database with backend server. | N/A | No | 11:00
6 | Set up the wiki and the repo for the next deliverable | Begin work on the web interface using react | *waves arms at everything* | Yes | 12:00
7 | Optimize Server and Front-end. Debug. Automatic tests. Three basic Object Class. (Post, User, Comment) | Server and Database connection. Fron-end Backend connection. | N/A | No | 2:02
7 | - Started working on login - Researched about hashing passwords in Javascript - Understand bcrypt documentation | - Debug login - Understand util functions for backend | No | Yes | 10:00
7 | Post functionality - front end | Login functionality | Non as of yet | No | 9:00
7 | front end overhaul, file cleanup, and nav bar + css | file uploading | no | Yes | 10:00
8 | DB part of Comment. Tests. | Tests; Report; etc. | N/A | No | 11:00
8 | - Login validation functions (user ID and password validation) | - Debugging and fixing current code issues - Report and wiki documentation | No | Yes | 10:00
8 | Login - front end | Login for super group | None | No | 10:00
8 | content uploading + issue resolving + bug fixing | start on report, fix more issues and help where I am needed | no | Yes | 10:00
9 | - Write report for Deliverable 2 - Testing and documentation - Login verification debugging | - Scrum reflection meeting | No | Yes | 10:00
9 | Frontend Interface Design. Backend Frontend communication. | Submit Deliverable2. Supergroup login. | N/A | No | 3:03
9 | Login-supergroup | Improve front end presentation | Deadlines for other moduels | No | 10:00
9 | started on report and content migration | continue on report and content migration alongside anything else that needs doing until we submit | my impending doom | Yes | 10:00